## Sheet1
Insert title
Work plan and budget
Research shows that thorough initial planning is an excellent indicator of successful project delivery.
This table is a planning tool for your use. It will support your application and show your organisations’ capacity to achieve your project outcomes.
Some example activities are provided for your in fomration. Please delete these activities and complete as required.
Instructions
Activities: Break your project down into specific activities. Identify what each activity will achieve and estimated start and finish times. Keep activities in a logical (chronological) order.
Resources: For each activity identify the materials, equipment, and labour you need and how much each will cost (if you are unsure, make an estimate).
Funding: Identify who will contribute to each part of the activity. In-kind and cash contributions from your group and others (including other grants) make up your co-contribution. Include any fees and charges or any fee waivers
# | Activities |  |  | Resources |  |  |  | Funding Source
| Describe what you will achieve | Start MM / YY | Finish MM / YY | Describe the materials, equipment and labour you need | Cost per unit $ (incl. GST) | Number required | Total cost $ (incl. GST) | Detail who will contribute to this activity. Include EMF contribution plus cash and in-kind contributions from your group and others including other grants (name grant). | Co-contributions (cash and in-kind) $ (incl. GST) | AMR Shire EMF grant $ (incl. GST)
1 | Rehabilitate creek in shire reserve | [5 empty] | 0
| Control blackberry and other weeds | 2023-11-01 | 2024-03-01 | Contractor | 70 | 30 | 3100 | EMF to entirely fund | 0 | 3100
|  |  |  | labour (Friends of Reserve volunteers) | 30 | 20 | 600 | reserve surveying and mapping | 600
| Revegetate 1 ha | 2024-04-01 | 2024-06-01 | Seedlings | 1000 | 2 | 2000 |  |  | 2000
|  |  |  | bags and stakes | 500 | 1.5 | 750 |  |  | 750
|  |  |  | labour (school children) | 15 | 100 | 1500 | 2 classes of 25 children for 2 hours each | 1500
|  |  |  | labour (Friends of Reserve volunteers) | 30 | 72 | 2160 | six volunteers for 3 hours for 4 weeks | 2160
0
| Increase capacity of Friends of Foreshore via training session on weed identification and mapping techniques | [5 empty] | 0
|  |  |  | contractor to provide training | 50 | 6 | 300 | 6 hours including preparation and | 300
|  |  |  | volunteers | 30 | 18 | 540 | 6 x 3 hours | 540
0
2 | [6 empty] | 0
3 | [6 empty] | 0
4 | promotion |  |  | promotion- 4 social media posts, 1 newspaper advertisment, 1 school newsletter | 250 | 1 | 250 |  |  | 250
5 | Indigenous engagement |  |  |  | 1000 | 1 | 1000 |  | 1000
| Total | [5 empty] | 12200 | Total | 6100 | 6100